## T-05 Power-Interest Grid
STAKEHOLDER ANALYSIS MATRIX — Power-Interest Grid
Template T-05 · Chapter 5: Stakeholder Management · radimkaufmann.com
ENGAGEMENT STRATEGIES
POWER ↑ |  | Interest 1 Very Low | Interest 2 Low |  | Interest 3 Medium | Interest 4 High | Interest 5 Very High |  | Quadrant | Strategy | Frequency | Tools
Power 5 ★★★★★ |  | 👁 KEEP SATISFIED High Power · Low Interest |  |  |  |  | 👤 MANAGE CLOSELY High Power · High Interest |  | Manage Closely High Power High Interest | Actively engage, involve in decisions | Weekly | Steering committee, 1:1 meetings, early sign-off
Power 4 ★★★★ | [8 empty] | Keep Satisfied High Power Low Interest | Keep happy, avoid surprises | Monthly | Executive summaries, milestone reports
Power 3 ★★★ | [8 empty] | Keep Informed Low Power High Interest | Provide updates, gather input | Bi-weekly | Newsletters, workshops, feedback sessions
Power 2 ★★ | [8 empty] | Monitor Low Power Low Interest | Minimal effort, watch for changes | Quarterly | Distribution list, general updates
Power 1 ★ |  | 👀 MONITOR Low Power · Low Interest |  |  |  |  | 📢 KEEP INFORMED Low Power · High Interest
← Low Interest ·· INTEREST ·· High Interest →
STAKEHOLDER PLACEMENT · List stakeholders and their grid position
# | Stakeholder Name |  | Power (1-5) | Interest (1-5) | Quadrant | Current Engagement | Action Required | Review Date
1 | Project Sponsor |  | 5 | 4 | Manage Closely | Supportive | Monthly exec briefing
2 | Customer Ops Mgr |  | 4 | 5 | Manage Closely | Neutral | Weekly status call
3 | IT Head |  | 3 | 4 | Manage Closely | Resistant | Early involvement
4 | End Users |  | 2 | 4 | Keep Informed | Unaware | Training + comms plan
5 | Regulator |  | 5 | 3 | Keep Satisfied | Neutral | Compliance reports
6 | Finance Dept |  | 3 | 2 | Monitor | Neutral | Quarterly updates
From "Project Management: From Initiation to Closure" by Radim Kaufmann · radimkaufmann.com · Free download