## T-06 WBS Worksheet
WORK BREAKDOWN STRUCTURE (WBS) WORKSHEET
Template T-06 · Chapter 6: Work Breakdown Structure · radimkaufmann.com
Project Title |  |  |  |  | PM / Owner |  |  |  | Date / Version
WBS Levels: L0=Project · L1=Phase/Major Deliverable · L2=Sub-deliverable · L3=Work Package · L4=Task ¦ 100% Rule: child items must cover 100% of parent scope — nothing more, nothing less
WBS Code | Lvl | ▸ | ▸▸ | Work Package / Task Description | Deliverable / Output | Owner | Hours | Cost ($) | Start | End | Status
1.0 | L0 |  |  | [PROJECT NAME] | Final Accepted System | PM |  |  |  |  | In Progress
1.1 | L1 |  |  | PHASE 1: INITIATION | Phase 1 Complete | PM | 40 | 4000
1.1.1 | L2 |  |  | Project Charter | Signed Charter | PM | 8 | 800
1.1.1.1 | L3 |  |  | Draft Charter | Charter Draft | PM | 4 | 400
1.1.1.2 | L3 |  |  | Review & Approve Charter | Approved Charter | Sponsor | 4 | 400
1.1.2 | L2 |  |  | Stakeholder Identification | Stakeholder Register | PM | 16 | 1600
1.1.3 | L2 |  |  | Kick-off Meeting | Kick-off Minutes | PM | 16 | 1600
1.2 | L1 |  |  | PHASE 2: PLANNING | Planning Documents | PM | 120 | 12000
1.2.1 | L2 |  |  | Scope Definition | Scope Statement | PM | 24 | 2400
1.2.1.1 | L3 |  |  | Requirements Gathering | Requirements Doc | BA | 16 | 1600
1.2.1.2 | L3 |  |  | Scope Statement Sign-off | Signed Scope Stmt | PM | 8 | 800
1.2.2 | L2 |  |  | Schedule Development | Baseline Schedule | PM | 24 | 2400
1.2.2.1 | L3 |  |  | WBS Creation | WBS Document | PM | 8 | 800
1.2.2.2 | L3 |  |  | Activity Sequencing & Estimating | Network Diagram | PM | 16 | 1600
1.2.3 | L2 |  |  | Budget & Risk Planning | Budget + Risk Register | PM | 32 | 3200
1.3 | L1 |  |  | PHASE 3: EXECUTION | Deliverables | PM
1.3.1 | L2 |  |  | [Add Work Package] | [Deliverable] | [Owner]
1.3.2 | L2 |  |  | [Add Work Package] | [Deliverable] | [Owner]
1.3.3 | L2 |  |  | [Add Work Package] | [Deliverable] | [Owner]
1.3.4 | L2 |  |  | [Add Work Package] | [Deliverable] | [Owner]
1.4 | L1 |  |  | PHASE 4: MONITORING & CONTROL | Control Documents | PM
1.4.1 | L2 |  |  | Status Reporting | Weekly Reports | PM
1.4.2 | L2 |  |  | Change Management | Change Log | PM
1.5 | L1 |  |  | PHASE 5: CLOSURE | Closed Project | PM
1.5.1 | L2 |  |  | Final Acceptance (PAC/FAC) | Acceptance Protocol | PM | 16 | 1600
1.5.2 | L2 |  |  | Lessons Learned | LL Report | PM | 8 | 800
1.5.3 | L2 |  |  | Project Closure Report | Final Report | PM | 8 | 800
TOTAL PROJECT ESTIMATE
From "Project Management: From Initiation to Closure" by Radim Kaufmann · radimkaufmann.com · Free download · 100% Rule: child items must equal 100% of parent scope