## T-07 Gantt Chart
GANTT CHART — PROJECT TIME PLAN
Template T-07 · Chapter 7: Time Planning and Scheduling · radimkaufmann.com
Project |  |  |  |  | PM |  |  |  |  | Start Date |  |  |  |  | End Date |  |  |  |  | Version
■ Planned bar ◆ Milestone ● % Complete ¦ Enter Start/End dates — bars shade automatically when you fill in planned weeks ¦ Week columns: W1=project week 1, etc.
[7 empty] | Month 1 |  |  |  | Month 2 |  |  |  | Month 3 |  |  |  | Month 4
ID | Task / Milestone | Owner | Start | End | Dur (d) | Done % | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16
1 | PROJECT KICKOFF ◆ | PM | W1 | W1 | 1 | 100% | ◆
1.1 | INITIATION | PM | W1 | W3 | 3 | 100%
1.1.1 | Project Charter | PM | W1 | W2 | 2 | 100%
1.1.2 | Stakeholder Register | PM | W2 | W3 | 2 | 100%
1.1.3 | Kick-off Meeting ◆ | PM | W3 | W3 | 1 | 100% |  |  | ◆
1.2 | PLANNING | PM | W3 | W7 | 5 | 80%
1.2.1 | Scope Statement | PM | W3 | W4 | 2 | 100%
1.2.2 | WBS & Schedule | PM | W4 | W5 | 2 | 100%
1.2.3 | Budget Plan | PM | W5 | W6 | 2 | 80%
1.2.4 | Risk Register | PM | W5 | W6 | 2 | 80%
1.2.5 | Communication Plan | PM | W6 | W7 | 2 | 50%
1.3 | EXECUTION | Team | W7 | W13 | 7 | 20%
1.3.1 | [Work Package 1] | [Owner] | W7 | W9 | 3 | 20%
1.3.2 | [Work Package 2] | [Owner] | W8 | W10 | 3
1.3.3 | [Work Package 3] | [Owner] | W10 | W12 | 3
1.3.4 | [Work Package 4] | [Owner] | W11 | W13 | 3
1.4 | MONITORING & CONTROL | PM | W1 | W16 | 16
1.4.1 | Weekly Status Reports | PM | W1 | W16 | 16
1.5 | CLOSURE | PM | W14 | W16 | 3
1.5.1 | UAT / Acceptance ◆ | PM | W14 | W15 | 2 | [14 empty] | ◆
1.5.2 | Lessons Learned | PM | W15 | W15 | 1
1.5.3 | Project Closure ◆ | PM | W16 | W16 | 1 | [16 empty] | ◆
LEGEND |  | Planned |  | Completed |  | Milestone |  | Today marker |  | Critical Path
From "Project Management: From Initiation to Closure" by Radim Kaufmann · radimkaufmann.com · Free download · ◆ = Milestone (zero duration)