## T-09 Resource Sheet
RESOURCE SHEET — Allocation & Availability Plan
Template T-09 · Chapter 9: Resource Planning · radimkaufmann.com
Project | [6 empty] | PM / Resource Manager | [8 empty] | Period
Allocation %: 100=full-time · 50=half-time · 0=unavailable ¦ Red = over-allocated (>100%) Orange = near capacity (80–100%) Green = allocated Gray = unallocated
[7 empty] | Month 1 |  |  |  | Month 2 |  |  |  | Month 3 |  |  |  | Month 4
Resource Name | Role / Title | Type | Department | Rate ($/hr) | Curr. | Avail % | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | Total Hrs | Over- Alloc?
Alex Johnson | Project Manager | Internal | PMO | 120 | USD | 100% | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
Maria Chen | Business Analyst | Internal | IT | 95 | USD | 80% | Month 1 W1: 80; Month 1 W2: 80; Month 1 W3: 80; Month 1 W4: 80; Month 2 W5: 80; Month 2 W6: 80; Month 2 W7: 80; Month 2 W8: 80
Tom Reeves | Developer | Internal | IT | 85 | USD | 100% | Month 1 W3: 50; Month 1 W4: 100; Month 2 W5: 100; Month 2 W6: 100; Month 2 W7: 100; Month 2 W8: 100; Month 3 W9: 100; Month 3 W10: 100; Month 3 W11: 100
Sarah Kim | QA Engineer | Internal | IT | 80 | USD | 50% | Month 2 W5: 50; Month 2 W6: 50; Month 2 W7: 50; Month 2 W8: 50; Month 3 W9: 100; Month 3 W10: 100; Month 3 W11: 100; Month 3 W12: 50
ExtCo Ltd | System Integrator | External | Vendor | 150 | USD | 100% | Month 1 W4: 50; Month 2 W5: 100; Month 2 W6: 100; Month 2 W7: 100; Month 2 W8: 100; Month 3 W9: 100; Month 3 W10: 100
Lisa Wang | Change Manager | Internal | HR | 90 | USD | 50% | Month 2 W7: 50; Month 2 W8: 50; Month 3 W9: 50; Month 3 W10: 50; Month 3 W11: 50; Month 3 W12: 100; Month 4 W13: 100; Month 4 W14: 100; Month 4 W15: 50
[Resource 7] | [Role] | Internal | [Dept] |  | USD | 100% | bar: Month 1 W3; Month 2 W5; Month 2 W7; Month 3 W9; Month 3 W11
[Resource 8] | [Role] | External | [Vendor] |  | USD | 100% | bar: Month 1 W3; Month 2 W5; Month 2 W7; Month 3 W9; Month 3 W11
TEAM WEEKLY TOTALS (sum of all allocations)
From "Project Management: From Initiation to Closure" by Radim Kaufmann · radimkaufmann.com · Free download · Green=allocated Orange=near capacity Red=over-allocated