## T-10 Project Budget
PROJECT BUDGET
Template T-10 · Chapter 8: Budget Planning and Cost Management · radimkaufmann.com
Project |  |  |  |  | PM |  |  |  | Currency |  | USD
Type: CAPEX = Capital Expenditure (assets) · OPEX = Operating Expenditure (running costs) ¦ Variance = Approved − Actual · Negative variance = over budget · Contingency typically 10–15% of base budget
Category | Sub-item / Description | WBS Ref | Type (CAP/OP) | Unit | Qty | Unit Cost ($) | Estimated ($) | Approved ($) | Actual ($) | Variance ($) | Notes
INTERNAL LABOR
| Project Manager | 1.0 | OPEX | Month | 6 | 8000 | 48000 | 48000 | 12000 |  | Full duration
| Business Analyst | 1.2.1 | OPEX | Month | 4 | 5500 | 22000 | 22000 | 8000 |  | Initiation+Planning
| Lead Developer | 1.3.1 | OPEX | Month | 6 | 7000 | 42000 | 42000 | 14000 |  | Execution phase
| QA Engineer | 1.3.2 | OPEX | Month | 3 | 5000 | 15000 | 15000 | 6000 |  | Testing phase
| Change Manager | 1.4 | OPEX | Month | 2 | 5500 | 11000 | 11000 | 2000
EXTERNAL / VENDORS
| System Integrator | 1.3.1 | OPEX | Day | 30 | 1200 | 36000 | 36000 | 9600 |  | Key vendor
| Legal / Contracts | 1.1 | OPEX | LS | 1 | 5000 | 5000 | 5000
| External Consulting | 1.2 | OPEX | Day | 10 | 900 | 9000 | 9000
HARDWARE / EQUIPMENT
| Servers (on-premise) | 1.3.1 | CAPEX | Unit | 3 | 8000 | 24000 | 24000
| Network Equipment | 1.3.1 | CAPEX | LS | 1 | 6000 | 6000 | 6000
| Workstations | 1.3 | CAPEX | Unit | 5 | 900 | 4500 | 4500
SOFTWARE / LICENSES
| Project Mgmt Tool | 1.0 | OPEX | Year | 1 | 2400 | 2400 | 2400 | 200 |  | Annual SaaS
| ERP Module License | 1.3.1 | CAPEX | LS | 1 | 18000 | 18000 | 18000
| Development Tools | 1.3 | OPEX | Year | 1 | 1200 | 1200 | 1200 | 100
TRAVEL & LOGISTICS
| Kick-off / Workshops | 1.1.3 | OPEX | Trip | 3 | 1500 | 4500 | 4500 | 1500
| Site Visits / FAT/SAT | 1.5.1 | OPEX | Trip | 4 | 2000 | 8000 | 8000
TRAINING
| End User Training | 1.4 | OPEX | Day | 5 | 1200 | 6000 | 6000
| Technical Training | 1.3 | OPEX | Day | 3 | 1500 | 4500 | 4500
CONTINGENCY (10%)
| Risk Contingency Reserve |  | OPEX | LS | 1 |  | 0 | 0 |  |  | Calculated below
Subtotal — INTERNAL LABOR
Subtotal — EXTERNAL / VENDORS
Subtotal — HARDWARE / EQUIPMENT
Subtotal — SOFTWARE / LICENSES
Subtotal — TRAVEL & LOGISTICS
Subtotal — TRAINING
Subtotal — CONTINGENCY (10%)
CONTINGENCY RESERVE (10% of base budget)
TOTAL PROJECT BUDGET (incl. contingency)
BUDGET HEALTH |  |  | Total Approved |  | Total Spent to Date |  | Remaining |  | % Spent
From "Project Management: From Initiation to Closure" by Radim Kaufmann · radimkaufmann.com · Free download · CAPEX=asset investment OPEX=running cost