## T-11 Cash Flow
CASH FLOW TABLE — Monthly Cost Plan
Template T-11 · Chapter 8: Budget Planning and Cost Management · radimkaufmann.com
Project |  |  |  |  | PM |  |  |  |  | Year |  | 2026 |  | Currency |  | USD
Enter planned spend per cost item per month · Cumulative row shows running total (S-curve base) · Planned vs Actual variance highlights over/under spend by month
|  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4
Category | Sub-item | Type | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | TOTAL | Notes
INTERNAL LABOR
| Project Manager | OPEX | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000
| Business Analyst | OPEX | 5500 | 5500 | 5500 | 5500
| Lead Developer | OPEX |  |  | 7000 | 7000 | 7000 | 7000 | 7000 | 7000
| QA Engineer | OPEX |  |  |  |  | 5000 | 5000 | 5000
| Change Manager | OPEX | [5 empty] | 5500 | 5500 | 5500 | 5500
EXTERNAL / VENDORS
| System Integrator | OPEX |  |  |  | 12000 | 12000 | 12000
| Legal / Contracts | OPEX | 5000
| External Consulting | OPEX |  | 4500 | 4500
HARDWARE / EQUIPMENT
| Servers | CAPEX |  |  | 24000
| Network Equipment | CAPEX |  |  | 6000
| Workstations | CAPEX |  |  | 4500
SOFTWARE / LICENSES
| Project Mgmt Tool | OPEX | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200
| ERP Module License | CAPEX |  |  |  | 18000
| Development Tools | OPEX | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
TRAVEL & LOGISTICS
| Kick-off / Workshops | OPEX | 1500 |  |  | 1500 |  |  | 1500
| Site Visits / FAT/SAT | OPEX | [7 empty] | 2000 | 2000 | 2000 | 2000
TRAINING
| End User Training | OPEX | [8 empty] | 6000
| Technical Training | OPEX | [5 empty] | 4500
CONTINGENCY
| Risk Reserve (monthly) | OPEX | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000
MONTHLY TOTAL (Planned)
ACTUAL SPEND (per month)
VARIANCE (Planned − Actual)
CUMULATIVE PLANNED (S-curve)
From "Project Management: From Initiation to Closure" by Radim Kaufmann · radimkaufmann.com · Free download · Cumulative row = S-curve baseline for EVM tracking