## T-12 RACI Matrix
RACI MATRIX — Responsibility Assignment
Template T-12 · Chapter 9: Team and Resource Management · radimkaufmann.com
Project |  |  |  |  | PM |  |  |  |  | Version / Date
R = Responsible (does the work) · A = Accountable (owns the outcome — max 1 per row) · C = Consulted (provides input before) · I = Informed (notified after) ¦ Rule: Every row must have exactly one A. Never leave a row without an R.
# | Phase | Activity / Deliverable | Project Manager | Project Sponsor | Business Analyst | Lead Developer | QA Engineer | IT Architect | Change Manager | Customer Rep | PMO | Vendor / External
1.1 | Initiation | Project Charter | A | R | C |  |  |  |  | I | C
1.2 | Initiation | Stakeholder Identification | R | I | A |  |  |  | C | C | I
1.3 | Initiation | Kick-off Meeting | R | A | C | I | I | I | C | C | I | I
2.1 | Planning | Scope Statement | A | C | R |  |  | C |  | C | I
2.2 | Planning | WBS Development | R | I | A | C |  | C |  |  | I
2.3 | Planning | Schedule (Gantt) | A | I | C | R |  | C |  | I | I
2.4 | Planning | Budget Plan | R: A; A: R; C: C; C: I; I: C
2.5 | Planning | Risk Register | R | C | A | C |  | C |  | I | I | C
2.6 | Planning | Communication Plan | R | I | C |  |  |  | A | C | I
2.7 | Planning | Resource Plan | A | C |  | R |  | C | C |  | I
3.1 | Execution | Detailed Design | C | I | A | R |  | R |  | C | I | C
3.2 | Execution | Development / Build | I | I | C | R | C | A |  | I | I | R
3.3 | Execution | System Integration | C | I |  | R | C | A |  | I | I | R
3.4 | Execution | Change Management | R | C | C |  |  |  | A | C | I
3.5 | Execution | Vendor Management | A | I |  |  |  | C |  | C | I | R
4.1 | Monitoring | Status Reporting | R | I |  | I | I | I | I | I | A
4.2 | Monitoring | Issue Management | A | C | C | R | R | C |  | I | I
4.3 | Monitoring | Change Control | A | R | C | C |  | C | C | C | I
4.4 | Monitoring | Risk Review | R | C | A | C |  | C |  | I | I
5.1 | Closure | UAT / Acceptance Testing | C | I | C | R | A | C |  | R | I
5.2 | Closure | PAC / FAC Sign-off | R: C; A: A; C: R; I: I
5.3 | Closure | Lessons Learned | R | C | C | C | C | C | C | I | A
5.4 | Closure | Project Closure Report | R: R; C: I; C: C; I: I; A: A
RACI SUMMARY — Count per role (R/A/C/I)
Count of 'R'
Count of 'A'
Count of 'C'
Count of 'I'
LEGEND |  | R — Responsible | C: A — Accountable; C: C — Consulted
From "Project Management: From Initiation to Closure" by Radim Kaufmann · radimkaufmann.com · Free download · Rule: exactly one A per row — never leave a row without R