## T-13 Team Composition
TEAM COMPOSITION SHEET
Template T-13 · Chapter 9: Team and Resource Management · radimkaufmann.com
Project |  |  |  |  | PM |  |  |  | Date
Type: Internal = own employee · External = vendor/contractor · Allocation %: planned effort on this project · From/To: assignment period on the project
# | Full Name | Role / Title | Type | Dept / Company | Alloc % | From (date) | To (date) | Reports To | Key Skills / Expertise | Contact / Email | Notes
1 | Alex Johnson | Project Manager | Internal | PMO | 100% | 01/01/26 | 31/12/26 | Project Sponsor | PM, Risk Mgmt, Agile, PMBOK | a.johnson@company.com | Full duration
2 | Maria Chen | Business Analyst | Internal | IT Dept | 80% | 01/01/26 | 30/06/26 | Alex Johnson | Requirements, Process Mapping, UAT | m.chen@company.com | Initiation+Planning
3 | Tom Reeves | Lead Developer | Internal | IT Dept | 100% | 01/03/26 | 31/10/26 | Alex Johnson | Java, Python, System Architecture | t.reeves@company.com | Execution phase
4 | Sarah Kim | QA Engineer | Internal | IT Dept | 50% | 01/05/26 | 30/09/26 | Alex Johnson | Test Planning, Automation, UAT | s.kim@company.com | Testing phase
5 | ExtCo Ltd | System Integrator | External | Vendor | 100% | 01/04/26 | 30/09/26 | Alex Johnson | SAP, ERP Integration, API | pm@extco.com | Key vendor — NDA signed
6 | Lisa Wang | Change Manager | Internal | HR Dept | 50% | 01/06/26 | 31/12/26 | Alex Johnson | Change Mgmt, Training, Comms | l.wang@company.com
7 | Dr. R. Fischer | IT Architect | Internal | IT Dept | 30% | 01/02/26 | 30/06/26 | CTO | Enterprise Architecture, Security | r.fischer@company.com | Part-time advisor
8 | James Okafor | Customer Rep | External | Customer | 20% | 01/01/26 | 31/12/26 | Customer VP | Operations, Acceptance Testing | j.okafor@customer.com | Customer liaison
9 | PMO Coordinator | PMO Support | Internal | PMO | 25% | 01/01/26 | 31/12/26 | PMO Head | Reporting, Templates, Governance | pmo@company.com
10 | [Resource 10] | [Role] | Internal | [Dept]
TEAM SUMMARY
Total Members |  | Internal |  | External |  | Full-time (100%) |  | Avg Allocation
From "Project Management: From Initiation to Closure" by Radim Kaufmann · radimkaufmann.com · Free download · Link to RACI Matrix (T-12) for role assignments