## T-15 Risk Register
RISK MANAGEMENT LIST — Risk Register
Template T-15 · Chapter 10: Risk Management · radimkaufmann.com
Project |  |  |  |  | PM / Risk Owner |  |  |  |  | Review Date
Probability & Impact Scale: 1=Very Low 2=Low 3=Medium 4=High 5=Very High ¦ Risk Score = Probability × Impact ¦ Rating: Critical ≥16 High 9–15 Medium 4–8 Low 1–3 ¦ Strategy: Avoid · Mitigate · Transfer · Accept
ID | Category | Risk Description | Trigger / Early Warning | Prob (1-5) | Impact (1-5) | Score (P×I) | Rating | Strategy | Response Action | Owner | Deadline | Res. Prob | Res. Impact | Status
R-01 | Scope | Underdefined requirements lead to scope creep during execution | Frequent change requests in planning phase | 5 | 4 |  | Critical | Avoid | Conduct thorough requirements workshop; freeze scope before execution kickoff | PM / BA | Q1 W4 | 2 | 2 | Open
R-02 | Schedule | Key developer unavailable due to illness or resignation | Team member absence >3 days; no backup named | 3 | 5 |  | High | Mitigate | Document knowledge; cross-train backup resource; add float to schedule | PM | Ongoing | 2 | 3 | Open
R-03 | Budget | Vendor costs exceed contracted price due to change orders | First vendor invoice higher than PO value | 4 | 4 |  | Critical | Transfer | Fixed-price contract with penalty clause; change order approval process | PM / Legal | Contract sign | 2 | 2 | Open
R-04 | Technical | System integration fails between ERP and new platform | API handshake errors in integration test | 4 | 5 |  | Critical | Mitigate | Early integration spike; dedicated integration testing environment; rollback plan | Architect | W8 | 2 | 3 | In Progress
R-05 | Stakeholder | Customer delays acceptance testing causing schedule slip | Customer UAT team not resourced on time | 3 | 4 |  | High | Mitigate | Agree UAT resource plan in project charter; weekly customer alignment calls | PM | Q2 W1 | 2 | 2 | Open
R-06 | Compliance | Regulatory change invalidates current design approach | Regulatory body announcement / consultation | 2 | 5 |  | High | Avoid | Monitor regulatory pipeline; include compliance review gate in planning phase | PM / Legal | Quarterly | 1 | 4 | Open
R-07 | Quality | Inadequate testing time compresses quality assurance | Schedule pressure forcing UAT shortcut | 3 | 4 |  | High | Mitigate | Protect UAT buffer in schedule; define minimum exit criteria for UAT | QA Lead | W12 | 2 | 2 | Open
R-08 | Resource | External vendor underperforms against SLA | Missed milestone by vendor; quality below spec | 3 | 4 |  | High | Transfer | Performance KPIs in contract; monthly vendor review; escalation process | PM / Vendor | Monthly | 2 | 2 | Open
R-09 | Technology | Cloud infrastructure outage impacts development environment | Service degradation alert from cloud provider | 2 | 3 |  | Medium | Accept | Local dev environment backup; disaster recovery playbook documented | IT Architect | W2 | 1 | 2 | Accepted
R-10 | Change | Organizational resistance to new system from end users | Negative feedback in training sessions; low adoption rate | 4 | 3 |  | High | Mitigate | Early engagement; change ambassador program; phased rollout with champions | Change Mgr | Ongoing | 2 | 2 | Open
R-11 | Budget | Currency exchange rate fluctuation on foreign vendor payments | FX rate movement >5% from budget assumption | 2 | 3 |  | Medium | Transfer | Hedge contract in base currency; include FX buffer in contingency | PM / Finance | Contract | 1 | 2 | Open
R-12 | Schedule | Regulatory approval takes longer than planned | No response from authority within expected window | 2 | 4 |  | Medium | Mitigate | Submit applications 6 weeks early; pre-consultation with authority | PM / Legal | W3 | 1 | 3 | Open
RISK SUMMARY
Total Risks |  | Critical (≥16) |  | High (9-15) |  | Medium (4-8) |  | Low (1-3) |  | Open |  | Closed/Mitigated
From "Project Management: From Initiation to Closure" by Radim Kaufmann · radimkaufmann.com · Free download · Review risks weekly during execution — use with T-16 Risk Matrix