## T-16 Risk Matrix
RISK MATRIX — 5×5 Probability / Impact Heat Map
Template T-16 · Chapter 10: Risk Management · radimkaufmann.com
Project | [6 empty] | PM / Risk Owner | [6 empty] | Review Date
Score = Probability × Impact ¦ Critical ≥16 (red) · High 9–15 (orange) · Medium 4–8 (yellow) · Low 1–3 (green) ¦ Plot each risk by ID in the grid cell — multiple risks can share a cell
|  | ← IMPACT → | [5 empty] | RISK PLACEMENT TABLE
PROBABILITY ↑ |  | 1 Very Low | 2 Low | 3 Medium | 4 High | 5 Very High |  | ID | Risk (short) | Prob | Impact | Score | Rating | Strategy | Response Owner | Status
5 Very High | Very High | 5 | 10 | 15 | R-01 | 25 |  | R-01 | Scope creep (req.) | 5 | 4 | 20 | Critical | Avoid | PM / BA | Open
4 High | High | 4 | 8 | R-08 R-10 | R-03 | R-04 |  | R-02 | Key dev. resign | 3 | 5 | 15 | High | Mitigate | PM | Open
3 Medium | Medium | 3 | 6 | 9 | R-05 R-07 | R-02 |  | R-03 | Vendor cost overrun | 4 | 4 | 16 | Critical | Transfer | PM / Legal | Open
2 Low | Low | 2 | 4 | R-09 R-11 | R-12 | R-06 |  | R-04 | ERP integration fail | 4 | 5 | 20 | Critical | Mitigate | Architect | In Progress
1 Very Low | Very Low | 1 | 2 | 3 | 4 | 5 |  | R-05 | Customer UAT delay | 3 | 4 | 12 | High | Mitigate | PM | Open
|  | ← Low Impact ·· IMPACT ·· High Impact → | [5 empty] | R-06 | Regulatory change | 2 | 5 | 10 | High | Avoid | PM / Legal | Open
[8 empty] | R-07 | Inadequate testing | 3 | 4 | 12 | High | Mitigate | QA Lead | Open
RISK RATING LEGEND | [7 empty] | R-08 | Vendor underperforms | 4 | 3 | 12 | High | Transfer | PM | Open
Critical ≥16 |  | Immediate action — escalate to sponsor | [5 empty] | R-09 | Cloud outage | 2 | 3 | 6 | Medium | Accept | IT Arch. | Accepted
High 9–15 |  | Urgent response plan required | [5 empty] | R-10 | User resistance | 4 | 3 | 12 | High | Mitigate | Change Mgr | Open
Medium 4–8 |  | Monitor closely — response plan needed | [5 empty] | R-11 | FX rate risk | 2 | 3 | 6 | Medium | Transfer | PM / Finance | Open
Low 1–3 |  | Monitor — review periodically | [5 empty] | R-12 | Regulatory delay | 2 | 4 | 8 | Medium | Mitigate | PM / Legal | Open
From "Project Management: From Initiation to Closure" by Radim Kaufmann · radimkaufmann.com · Free download · Use with T-15 Risk Register for full risk management