## T-18 Communication Matrix
COMMUNICATION MATRIX — Project Communication Plan
Template T-18 · Chapter 11: Communication Management · radimkaufmann.com
Project |  |  |  |  | PM / Comms Owner |  |  |  | Version / Date
Format: Report · Email · Meeting · Dashboard · Presentation · Call ¦ Channel: Email · Teams · Slack · SharePoint · In-Person · Video Call ¦ Feedback: Yes = two-way communication required
ID | Communication / Event | Purpose | Audience / Recipients | Frequency | Format | Channel | Owner | Timing | Feedback Required? | Notes
ROUTINE STATUS COMMUNICATIONS
C-01 | Weekly Status Report | Inform stakeholders of progress, issues, risks | PM, Sponsor, Customer | Weekly | Report (PDF) | Email | PM | Every Monday 09:00 | Yes | Use T-20 template
C-02 | Daily Stand-up | Team synchronization — progress, blockers | Project Team | Daily | Meeting | Video Call / In-Person | PM | 09:00 daily | No | 15 min max; Scrum format
C-03 | Bi-weekly Team Meeting | Detailed progress review, decisions, alignment | Full Project Team | Bi-weekly | Meeting | In-Person / Teams | PM | Every 2nd Wednesday | Yes | Use T-19 Minutes template
C-04 | Monthly Executive Report | High-level status for leadership decision-making | Executive Sponsor, Steering Committee | Monthly | Presentation | In-Person | PM | Last Friday of month | Yes | RAG status summary
STAKEHOLDER COMMUNICATIONS
C-05 | Customer Progress Call | Customer alignment — scope, schedule, open issues | Customer Representative, PM | Weekly | Meeting | Video Call | PM | Every Tuesday 14:00 | Yes | Record action items
C-06 | Vendor Review Meeting | Vendor performance, SLA tracking, escalations | PM, Vendor PM | Monthly | Meeting | Video Call / In-Person | PM | 1st Monday of month | Yes | Attach KPI report
C-07 | Steering Committee Update | Strategic decisions, budget approval, risk escalation | Steering Committee, Sponsor, PM | Monthly | Presentation | In-Person | PM | Last Thursday of month | Yes | Decision log mandatory
C-08 | Stakeholder Newsletter | General awareness update for wider audience | All Stakeholders | Monthly | Email | Email | Change Mgr | 1st week of month | No | Max 1 page; plain language
MILESTONE & EVENT COMMUNICATIONS
C-09 | Project Kick-off Meeting | Formally launch project; align all parties on plan | All Stakeholders | Once | Meeting | In-Person | PM | Project Week 1 | Yes | Use agenda template
C-10 | Quality Gate Review | Formal gate assessment before phase transition | PM, Sponsor, PMO, Customer | Per gate | Presentation | In-Person | PM | End of each phase | Yes | Gate criteria checklist
C-11 | Risk Review Session | Update risk register; review mitigation status | PM, Risk Owners, Team | Bi-weekly | Meeting | Teams | PM | Every 2nd Friday | Yes | Use T-15 / T-16
C-12 | Change Request Communication | Inform affected parties of approved changes | All impacted stakeholders | Ad-hoc | Email + Report | Email | PM | Within 24hrs of approval | Yes | Use T-24 Change Request
CLOSURE COMMUNICATIONS
C-13 | Acceptance Notification | Formal notification of PAC/FAC acceptance | Customer, Sponsor, Team | Milestone | Email + Report | Email | PM | Upon acceptance | No | Attach signed PAC/FAC
C-14 | Lessons Learned Workshop | Capture lessons for organizational learning | Full Project Team | Once | Meeting | In-Person | PM | Week before closure | Yes | Use T-26 template
C-15 | Project Closure Report | Final summary — scope, cost, schedule, lessons | All Stakeholders | Once | Report | Email | PM | Project close date | No | Use T-27 template
COMMUNICATION SUMMARY
Total Items |  | Two-way |  | Daily/Weekly |  | PM Owned |  | Milestone
From "Project Management: From Initiation to Closure" by Radim Kaufmann · radimkaufmann.com · Free download · Review and update this plan at each project phase