## T-20 Status Report
PROJECT STATUS REPORT
Template T-20 · Chapter 11: Communication Management · radimkaufmann.com
Project | [5 empty] | PM |  |  |  | Report #
OVERALL PROJECT STATUS
Reporting Period |  |  | Report Date |  |  | Next Report |  |  | Phase
OVERALL |  | SCOPE |  | SCHEDULE |  | BUDGET |  | QUALITY |  | RISK
● GREEN |  | ● GREEN |  | ● AMBER |  | ● GREEN |  | ● GREEN |  | ● AMBER
EXECUTIVE SUMMARY
Key highlights this period (2-3 sentences for executive audience):
KPI DASHBOARD
KPI |  |  | Target |  | Actual |  | Variance |  | Trend |  | Status
Schedule Performance Index (SPI) |  |  | ≥ 1.0 |  | 0.98 |  | –0.02 |  | → |  | AMBER
Cost Performance Index (CPI) |  |  | ≥ 1.0 |  | 1.02 |  | +0.02 |  | ↑ |  | GREEN
% Milestones On Time |  |  | 100% |  | 91% |  | –9% |  | ↓ |  | AMBER
Open Issues (Critical) |  |  | 0 |  | 2 |  | 2 |  | → |  | RED
Open Risks (High/Critical) |  |  | ≤ 3 |  | 4 |  | +1 |  | ↓ |  | AMBER
% Deliverables Accepted |  |  | On track |  | 72% |  |  |  | ↑ |  | GREEN
Team Utilization |  |  | 80–100% |  | 87% |  | +7% |  | → |  | GREEN
Change Requests Pending |  |  | 0 |  | 1 |  | 1 |  | → |  | AMBER
SCHEDULE HIGHLIGHTS
Milestone |  |  |  | Planned |  | Forecast |  | Status |  | Comment
Project Kick-off |  |  |  | 01/01/26 |  | 01/01/26 |  | DONE |  | On time
Planning Complete |  |  |  | 28/02/26 |  | 28/02/26 |  | DONE |  | On time
Design Approved |  |  |  | 15/03/26 |  | 17/03/26 |  | DONE |  | 2 days late
Development Start |  |  |  | 01/04/26 |  | 01/04/26 |  | IN PROGRESS |  | On track
UAT Start |  |  |  | 01/06/26 |  | 03/06/26 |  | FORECAST |  | 2 days slip
PAC / Acceptance |  |  |  | 30/06/26 |  | 30/06/26 |  | PLANNED
TOP ISSUES & RISKS THIS PERIOD
ID | Description |  |  |  |  | Impact |  | Owner |  | Status
I-01 | Customer UAT team not confirmed — risk to June acceptance |  |  |  |  | High |  | PM |  | Escalated
R-04 | ERP integration complexity higher than estimated |  |  |  |  | High |  | Architect |  | Mitigating
I-02 | License procurement delayed 2 weeks |  |  |  |  | Medium |  | PM |  | In Progress
R-02 | Key developer sick W13 — backup needed |  |  |  |  | High |  | PM |  | Open
BUDGET SNAPSHOT
Approved Budget |  |  | Spent to Date |  |  | Remaining |  |  | % Spent
$267,000 |  |  | $89,000 |  |  | $178,000 |  |  | 33.3%
NEXT STEPS (coming 2 weeks)
Action | [5 empty] | Owner |  | Due |  | Priority
H / M / L
H / M / L
H / M / L
H / M / L
From "Project Management: From Initiation to Closure" by Radim Kaufmann · radimkaufmann.com · Free download · RAG: Green=On Track Amber=At Risk Red=Off Track