## T-21 Issue Log
ISSUE LOG — Project Issue Tracker
Template T-21 · Chapter 12: Issue and Delivery Management · radimkaufmann.com
Project |  |  |  |  | PM / Issue Manager |  |  |  |  | Last Updated
Priority: Critical = blocks delivery · High = major impact · Medium = workaround exists · Low = minor ¦ Status: Open · In Progress · Escalated · Resolved · Closed ¦ Log every issue; never manage issues verbally
Issue ID | Date Raised | Raised By | Category | Issue Description | Impact on Project | Priority | Owner | Due Date | Resolution / Action | Status | Closed Date | Risk / CR Ref
I-001 | 03/01/26 | Customer Ops | Scope | Customer requesting additional reporting module not in scope statement | Scope increase — 3 days effort + cost impact | High | PM | 10/01/26 | Raise Change Request CR-001; present impact to steering committee | Open |  | CR-001
I-002 | 10/01/26 | IT Architect | Technical | API endpoint for ERP integration returns timeout after 30 seconds — intermittent | Integration testing blocked; risk to schedule | Critical | Architect | 15/01/26 | Vendor engaged; workaround via batch processing implemented | In Progress |  | R-04
I-003 | 15/01/26 | PM | Stakeholder | IT Head resistant to new system — blocking infrastructure provisioning | Infrastructure not ready; development start at risk | High | PM | 20/01/26 | Escalated to Sponsor; alignment meeting scheduled | Escalated
I-004 | 18/01/26 | BA | Scope | Requirements document v1.2 not signed off — customer delayed review by 2 weeks | Planning phase closure delayed | Medium | BA | 25/01/26 | Chasing customer; interim sign-off requested for planning to proceed | In Progress
I-005 | 22/01/26 | QA Lead | Technical | Test environment configuration differs from production — incorrect database version | Test results may not be representative | High | QA Lead | 28/01/26 | IT provisioning updated environment; re-run smoke tests | Resolved | 29/01/26
I-006 | 25/01/26 | PM | Resource | Business Analyst assigned to another project from March without backfill confirmed | BA availability drops to 20% during critical planning phase | High | PM | 01/02/26 | Resource manager notified; requesting replacement or timeline extension | Open
I-007 | 28/01/26 | Vendor PM | Vendor | Vendor unable to deliver integration module by agreed date — 3-week slip | UAT start date pushed to June 3; cascade impact on acceptance | Critical | PM | 30/01/26 | Vendor issued formal notice; penalty clause invoked; recovery plan requested | Open |  | R-08
I-008 | 01/02/26 | Change Mgr | Stakeholder | End user training materials not yet approved by customer training department | Training delivery at risk before go-live | Medium | Change Mgr | 15/02/26 | Revised materials submitted; feedback cycle agreed at 5 days | In Progress
I-009 | 03/02/26 | Finance | Budget | FX rate movement increases vendor contract cost by approximately $8,000 | Budget contingency partially consumed | Low | PM | 10/02/26 | Contingency buffer covers; documented in budget log | Resolved | 05/02/26 | R-11
I-010 | 05/02/26 | QA Lead | Process | No formal UAT entry criteria defined — risk of premature UAT start | UAT quality gate may be bypassed under schedule pressure | High | QA Lead | 12/02/26 | UAT entry criteria document drafted; requires PM and customer sign-off | Open
ISSUE SUMMARY
Total Issues |  | Open |  | In Progress |  | Escalated |  | Critical |  | Resolved/Closed
From "Project Management: From Initiation to Closure" by Radim Kaufmann · radimkaufmann.com · Free download · Review all open issues weekly in status meeting