## T-25 Lessons Learned Log
LESSONS LEARNED LOG
Template T-25 · Chapter 16: Project Closure · radimkaufmann.com
Project |  |  |  |  | PM / Facilitator |  |  |  | Session Date
Type: Positive = what worked well (repeat this) · Negative = what went wrong (avoid this) · Suggestion = improvement idea ¦ Status: Draft · Reviewed · Approved · Shared to Knowledge Base
LL-ID | Date | Phase | Category | Type | What Happened (Situation) | Root Cause / Why It Happened | Impact | Recommendation for Future Projects | Owner | Status
LL-001 | 17/03/26 | Initiation | Stakeholder | Negative | IT Head not included in initial stakeholder mapping — discovered resistance only at infrastructure provisioning stage | Stakeholder analysis (T-04) was completed too quickly without input from all department heads | High — 2-week delay in infrastructure readiness | Always include all department heads in initial stakeholder mapping. Conduct a stakeholder interview round before finalising T-04. | PM | Approved
LL-002 | 17/03/26 | Planning | Scope | Negative | Requirements document required 3 revision cycles before customer sign-off — planned for 1 | Requirements workshop was held once; customer stakeholders were not all present | Medium — 2-week planning delay | Hold requirements workshops in at least 2 rounds. Confirm all decision-makers are present before the first session. | BA | Approved
LL-003 | 17/03/26 | Execution | Technical | Negative | ERP API integration was more complex than estimated — caused a 3-week schedule impact | Integration complexity was assessed based on vendor documentation only, without a technical spike | High — 3-week delay + €12,000 additional cost | Always run a 1-week technical spike for any third-party integration before committing to estimates. Include Architect in bid/no-bid assessment. | Architect | Approved
LL-004 | 17/03/26 | Execution | Vendor | Negative | Vendor missed contracted delivery date by 3 weeks without early warning | Vendor reporting was monthly; no early warning mechanism in place | High — cascading impact on UAT and acceptance | Include weekly vendor check-ins from Week 4 of execution. Add contractual milestone reporting obligation to all vendor contracts. | PM | Approved
LL-005 | 17/03/26 | Planning | Risk | Positive | Pre-mortem workshop (T-17) in Week 3 of planning surfaced 4 risks that were not on the initial risk register | Structured facilitation allowed team members to voice concerns they had not raised informally | Positive — risks mitigated before execution | Run pre-mortem workshop as standard practice at the end of planning for all Category C and D projects. | PM | Approved
LL-006 | 17/03/26 | Execution | Team | Positive | Daily stand-ups during execution phase improved issue resolution speed significantly | Short daily format forced issues to be surfaced same-day rather than waiting for weekly status meeting | Positive — average issue resolution time reduced from 4 days to 1.5 days | Maintain daily stand-ups during execution phases of all projects. 15 minutes maximum. Use T-19 action items as input. | PM | Approved
LL-007 | 17/03/26 | Monitoring | Communication | Suggestion | Customer felt uninformed between bi-weekly calls — contacted PM directly by phone multiple times | Communication matrix did not include a customer-facing status dashboard | Low — no delivery impact but customer satisfaction affected | Add a read-only live dashboard or SharePoint status page for the customer in all future projects. Update weekly. | PM | Reviewed
LL-008 | 17/03/26 | Planning | Schedule | Negative | Buffer time was not built into the UAT phase — any vendor delay cascaded directly to acceptance | Schedule was optimistic; dependencies between vendor delivery and UAT start were not adequately buffered | High — UAT compressed from 3 weeks to 10 days | Always add minimum 20% buffer to phases that depend on external deliveries. Model best/worst case scenarios in Gantt (T-07). | PM | Approved
LL-009 | 17/03/26 | Closure | Process | Positive | Structured handover checklist (T-22 Delivery Report) prevented two missing documentation items from slipping through at PAC | Checklist forced systematic review of all handover items before acceptance meeting | Positive — acceptance completed without rework | Use T-22 Delivery Report for all milestone deliveries, not only final acceptance. Adapt Section 7 for each delivery type. | QA Lead | Approved
LL-010 | 17/03/26 | Execution | Budget | Suggestion | Budget tracking was manual (Excel); actual vs. planned comparison required significant PM effort each week | No integration between time sheets (T-08) and budget template (T-10) | Low — 2-3 hours/week PM overhead | Invest in project management tool (MS Project, Smartsheet, or equivalent) for projects >6 months. Link time tracking to budget automatically. | PMO | Draft
LL-011 | 17/03/26 | Planning | Team | Positive | Competency matrix (T-14) identified QA skill gap before execution — training was arranged proactively | Gap identified in planning phase; 2-week training completed before testing phase started | Positive — testing quality improved; no defects attributable to skill gap | Run T-14 Competency Matrix assessment at project start for all execution team members. Use results to drive training plan. | PM | Approved
LL-012 | 17/03/26 | Execution | Risk | Suggestion | Risk register (T-15) was not reviewed weekly as planned — fell to bi-weekly | Risk review depended on PM initiative; no calendar reminder or governance enforcement | Low — two risks escalated without early warning | Add risk review as standing agenda item in weekly status meeting (T-19). Make T-15 update a gate criterion for weekly report (T-20). | PM | Reviewed
LESSONS LEARNED SUMMARY
Total |  | Positive |  | Negative |  | Suggestions |  | Approved
From "Project Management: From Initiation to Closure" by Radim Kaufmann · radimkaufmann.com · Free download · Capture lessons throughout the project, not only at closure